## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2 | Notes | Total | Hania | Karim | Islam | Gomana | Ismail | Clara | Omar | Hagar | Rawi | Lobna | Nagy
1.1 | As a partner I should be able to submit a task/project with description so I can find candidates (add contact info) | 3 | Hania | Ismail | Hagar |  | 87 | 6 | 9 | 6 | 9 | 8 | 9 | 11 | 9 | 6 | 6 | 8
1.1.1 | As a partner I should be able to negotiating with admins (description) | 2 | Karim | Ismail | Hagar
1.2 | As a partner I should be able to view the status (lifecycle) of my task so i can track my task (lifecycle system) | 3 | Lobna | Ismail | Hagar
1.3 | As a partner i should be able to send a task orientation invitation so i can invite applicants | 3 | Hania | Ismail | Hagar
1.4 | As a partner I should be able to edit attributes to projects i have already posted so i can update the description and skills needed | 3 | Lobna | Ismail | Karim
1.5 | As a candidate, I should be able to create a profile | 2 | Omar | Ismail | Karim | Mostly front end, read from CRUD
1.6 | As a candidate, I should be able to login on the website | 5 | Omar | Ismail | Karim | Not now , front end and tokens later on
1.7 | As a candidate I should be able to search for tasks/projects so i can obtain a job | 3 | Gomana | Ismail | Karim
1.7.2 | As a candidate I should be able to view tasks/projects so i can obtain a job | 2 | Nagy | Islam | Karim
1.7.3 | As a candidate I should be able to apply (if qualified) to tasks/projects so i can obtain a job | 3 | Islam | Nagy | Hania
1.8.1 | As a candidate I should be accepted (or rejected) for a task/project and receive a task orientation | 3 | Islam | Nagy | Hania
1.8.2 | Notification system | 8 | Ismail | Nagy | Gomana
1.9 | As a candidate I should be able to update my progress on a task so it’s lifecycle is visible to everyone | 3 | Gomana | Nagy | Gomana
2 | As a candidate I should be able to view recommendations of tasks that match my skill set so i can get better results | EPIC
2.1 | As an admin I should be able to check description and finalize posting after negotiating with partner | 2 | Karim | Nagy | Gomana
2.1.1 | negotiation from the admin side | 5 | Karim | Nagy | Gomana
2.2 | As a Consultant I should be able to check description and finalize posting after negotiating with partner | 2 | Nagy | Islam | Lobna
2.3 | As an admin I should be able to assign which candidates get accepted to their applications so that i can facilitate the lifecycleof the task | 3 | Gomana | Nagy | Lobna
2.4 | As an admin I should be able to send a notification to anyone who registers so they can come and sign a contract | 2 | Omar | Nagy | Lobna
2.5 | As an admin I should be able to add signature time to candidate profile | 2 | Omar | Nagy | Lobna
2.6 | Create a Consultant | 1 | Nagy | Islam | Rawi
2.6.2 | Read a Consultant | 1 | Nagy | Islam | Rawi
2.6.3 | Update a Consultant | 1 | Nagy | Islam | Rawi
2.6.4 | Delete a Consultant | 1 | Nagy | Islam | Rawi
3 | Live Events
3.1 | As a partner I should be able to request to organize an event with location, description, registration price, remaining places, speakers and topics covered so that i can host an event | 5 | Hagar | Islam | Hania
3.1.2 | As an admin I should be able to request to organize an event with location, description, registration price, remaining places,speakers and topics covered so that i can host an event | 1 | Hagar | Islam | Hania
3.3 | As an admin i should be able to confirm a live event so that i can let the partner host the event and notify | 3 | Hagar | Nagy | Clara
3.4 | As a member I should be able to book applicable events so that i can attend events | 2 | Clara | Nagy | Omar
3.4.1 | As a member I should be able to view applicable events so that i can attend events | 2 | Clara | Nagy | Omar
3.4.2 | As a member i should be able to view the location, description, registration price, remaining places, speakers and topics , covered and know if applying is applicable so that i can attend events | 2 | Clara | Nagy | Omar
3.5.1 | As a member a record of the events I attended should be constantly updated so that i can track which events I’ve been to. | 3 | Clara | Nagy | Omar
3.6 | As a member I should be prompted to fill a feedback form after an event i attended is over so that i can provide feedback for the host (Form site) | 3 | Rawi | Nagy | Clara
3.7 | As a member i should be recommended events based on my interests and past events and locations so that i can attend events | 3 | Rawi | Nagy | Clara