## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Create a Task | 3 | Hania | -
1.1 | Read a Task | 3 | Lobna | 1 | Task needs to be created
1.2 | Update a Task | 3 | Lobna | 1 | Task needs to be created
1.3 | Delete a Task | 3 | Hania | 1 | Task needs to be created
2 | Create a Live Event | 3 | hagar | -
2.1 | Read a Live Event | 3 | nagy | 2 | Live event needs to be created
2.2 | Update a Live Event | 3 | hagar | 2 | Live event needs to be created
2.3 | Delete a Live Event | 3 | hagar | 2 | Live event needs to be created
3 | create a user | 3 | omar | -
3.1 | read a user | 3 | nagy | 3 | User needs to be created
3.2 | update a user | 3 | Karim | 3 | User needs to be created
3.3 | delete a user | 3 | Karim | 3 | User needs to be created
4 | create a partner | 3 | Karim | 3 | User needs to be created
4.1 | read a partner | 3 | nagy | 4 | Partner needs to be created
4.2 | update a partner | 3 | Karim | 4 | Partner needs to be created
4.3 | delete a partner | 3 | Karim | 4 | Partner needs to be created
5 | create a candidate | 3 | Gomana | 3 | User needs to be created
5.1 | read a candidate | 3 | Gomana | 5 | Candidate needs to be created
5.2 | update a candidate | 3 | Gomana | 5 | Candidate needs to be created
5.3 | delete a candidate | 3 | Gomana | 5 | Candidate needs to be created
6 | create an admin | 3 | Gomana | 3 | User needs to be created
6.1 | read an admin | 3 | nagy | 6 | admin needs to be created
6.2 | update an admin | 3 | Karim | 6 | admin needs to be created
6.3 | delete an admin | 3 | Ismail | 6 | admin needs to be created
7 | create a notification | 3 | Ismail | -
7.1 | read a notification | 3 | ismail | -
7.2 | update a notification | 3 | ismail | -
7.3 | delete a notification | 3 | ismail | -
8 | create a booking | 3 | Clara | Task 2 | An event needs to be created before I can book it
8.1 | read a booking | 3 | Clara | 8 | A booking has to be created
8.2 | update a booking | 3 | Clara | 8 | A booking has to be created
8.3 | delete a booking | 3 | Clara | 8 | A booking has to be created
9 | create an application | 3 | islam | -
9.1 | read an application | 3 | nagy | 9 | Appilcation needs to be created
9.2 | update an application | 3 | ismail | 9 | Appilcation needs to be created
9.3 | delete an application | 3 | Rawi | 9 | Appilcation needs to be created
10 | create a feedback form | 3 | Rawi | 2 | event needs to be created
10.1 | read a feedback form | 3 | Rawi | 10 | feedback from needs to be created
10.2 | update a feedback form | 3 | Rawi | 10 | feedback from needs to be created
10.3 | delete a feedback form | 3 | Rawi | 10 | feedback from needs to be created