## Sheet1
Team Name: Team 404
Project: Lirten Hub
Module: Task Management and Live Events
Scrum ID: 40-905
Scrum e-mail: islam.sanad@student.guc.edu.eg
Unique ID | User Story | Points | Epic | Priority
1 | Task Management
1.1 | As a partner I should be able to submit a task/project with description so I can find candidates (add contact info) | 3 | No | High
1.1.1 | As a partner I should be able to negotiating with admins (description) |  | No | Medium
1.3 | As a partner I should be able to view the status (lifecycle) of my task so i can track my task (lifecycle system) | 5 | No | Medium
1.4 | As a partner i should be able to send a task orientation invitation so i can invite applicants | 3 | No | Low
1.5 | As a partner I should be able to edit attributes to projects i have already posted so i can update the description and skills needed | 5 | No | Low | ask lirten if we need to renogiatie , we can redirect to the negotiation shit
1.6 | As a candidate, I should be able to create a profile | 5 | No | High
1.7 | As a candidate, I should be able to login on the website | 3 | No | High
1.8 | As a candidate I should be able to view, search and apply (if qualified) to tasks/projects so i can obtain a job |  | No | High
1.8.1 | View | 3
1.8.2 | search | 5
1.8.3 | apply | 3
1.9.1 | As a candidate I should be accepted (or rejected) for a task/project and receive a task orientation | 3
1.9.2 | Notification system | 8
2 | As a candidate I should be able to update my progress on a task so it’s lifecycle is visible to everyone | 5 | No | Medium
2.1 | As a candidate I should be able to view recommendations of tasks that match my skill set so i can get better results |  | Yes | Low
2.2 | As an admin I should be able to check description and finalize posting after negotiating with partner | 3
2.2.1 | negotiation from the admin side | 5 | No | High
2.3 | As an admin I should be able to assign which candidates get accepted to their applications so that i can facilitate the lifecycle | 3
| of the task |  | No | High
3 | Live Events
3.1 | As a partner I should be able to request to organize an event with location, description, registration price, remaining places, | 3
| speakers and topics covered so that i can host an event | 3 | No | High
3.2 | As an admin I should be able to request to organize an event with location, description, registration price, remaining places,
| speakers and topics covered so that i can host an event |  | No | High
3.3 | As an admin i should be able to confirm a live event so that i can let the partner host the event and notify | 3 | No | High
3.4 | As a member I should be able to view and book applicable events so that i can attend events | 3 | No | High
3.4.1 | Viewing system
3.4.2 | Booking system
3.5 | As a member i should be able to view the location, description, registration price, remaining places, speakers and topics , covered and know if applying is applicable so that i can attend events | 3
3.5.1 | validation system | 5 | No | High
3.6 | As a member a record of the events I attended should be constantly updated so that i can track which events I’ve been to. | 3 | No | Medium
3.7 | As a member I should be prompted to fill a feedback form after an event i attended is over so that i can provide feedback for the host (Form site) | 3
3.8 | As a member i should be recommended events based on my interests and past events and locations so that i can attend events |  | Yes | Low